Scope of Work

- Project Goals: The goal of this project is to provide an analysis of air quality data from across Nebraska for a request for proposal from the UNMC Water, Climate, and Health working group. The client has asked for the following analyses: (1) an overall statistical analysis to determine the five locations with the highest mean and median concentrations of VOC, PM 2.5, and PM 10.0, (2) an analysis of when and where maximum values of VOC, PM 2.5, and PM 10.0 occurred, and research of potential causes, (3) an analysis into the effects temperature and humidity has on air quality, and (4) if there have been any Air Quality Index (AQI) health risks at any location for PM 2.5 and PM 10.0 based on the EPA’s AQI ratings.

- Project Tasks:

- Task 1: Statistical analysis to determine locations with highest mean and median concentrations of pollutants.

- Data will be imported into Python, then grouped by location. A statistical analysis will then be run to calculate the mean and median of each pollutant at each site. The sites with the five highest values for each mean and median will then be selected.

- Task 2: Find when and where maximum values of pollutants occurred, and investigate potential causes.

- Using the data imported in (1), it will be grouped by both location and date. A statistical analysis will then be ran to find the maximum values of pollutants. Additionally, research will be conducted into potential causes of these maximum values such as natural diaster.

- Task 3: Determine if temperature or humidity have an impact on air quality.

- Using the data imported in (1), it will be grouped based on temperature and humidity. Temperature will be grouped <32F, 32-50, 51-70, >70. Humidity will be grouped <50%, 50-80%, >80%. Statistical analysis of each group will be ran to find the mean and median of pollutants at each temperature and humidity. Each group will be compared to the other temperature and humidity groups and the overall averages from (1) to determine if the temperature and humidity have an effect on air quality.

- Task 4: Determine if there have been any AQI health risks.

- Using the data imported in (1), it will be filtered based on EPA AQI ratings to find values that exceed the ratings. The date of each health risk will also be obtained. Additionally, research will be performed to determine potential causes of the health risks.

- Task 5: Determine if sensor altitude has an effect on air quality.

- Using the data imported in (1), it will be grouped based on altitude. A statistical analysis will then be ran to find the mean and median values at each altitude. These values will then be compared against other averages found to determine if the altitude had an effect.